## Sheet1
Nutrition Program Staff/Volunteer Training
PROJECT PLAN - TASK GRID
REGION:
TRAINING DATE:
LOCATION:
| WHAT - Task | Due Date | Date Completed | WHO - Responsibility | NOTES - Comments
Determine who will be planning committee lead (main contact person)
| Set dates for regional planning committee to meet or have conference calls | As needed |  | All regional planning committee members
| Determine the date and location for the training - Secure the site - Obtain approval from BADR & AAAs for date and location of training - Establish a contact person for training location logistics - Determine who will be responsible for arranging technical/audiovisual equipment needed for the training | 1/1/2019-7/12/2019
Designate Fiscal Agent
Select food provider for the training - Determine who will be main contact for food/beverage (provide meal counts, etc.) - Plan menu for lunch, morning refreshments, etc.
| Send a SAVE THE DATE to all your staff/volunteers that may be attending the training |  |  | All regional planning committee members
Develop training agenda - Approach, arrange, and book speakers
Develop budget for training - How much funding will need to be requested? - Determine registration fee
| Submit initial budget to BADR and AAA(s) for review and approval | 1 month before training OR by 8/16/2019 |  | Fiscal Agent
Finalize training agenda
Sent out registration information, menu, and agenda to nutrition directors in the region
| Collect attendee registration forms and fees - Send list of registrants to committee member responsible for registration on the day of the training - Collect fees and give to fiscal agent | Registration deadline established by the committee
Prepare nametags
Prepare attendance certificates (if applicable)
| Submit training plan and Planning Team Sign-Up Sheet to BADR and AAA(s) for review and approval | 1 month before training OR by 8/16/2019
Follow-up with all presenters to obtain speaker information
Customize the evaluation form with presentation titles and speakers names.
Make technical/audiovisual arrangements with venue
Obtain or purchase supplies/materials - Attendee folders - Door prizes and/or giveaways (if applicable)
Print handouts and compile attendee folders - Agenda - Evaluation form
Bring door prizes and/or giveaways to training (if applicable)
| Attend regional training | May 15th - November 15th |  | All regional nutrition directors (planning committee members)
Register attendees at training - Provide folders and handouts as appropriate.
Emcee the training throughout the day
Oversee food/beverage on day of training
Oversee technical/audiovisual on day of training
Collect evaluation forms from attendees
| Prepare list of attendees (including home county/tribe) | Within 30 days after training
| Provide receipts for reimbursement to the fiscal agent |  |  | All regional planning committee members
| Prepare final budget/expenditures form and invoice(s) for reimbursement (to GWAAR, WAND) | Within 30 days after training |  | Fiscal Agent
| Compile and tally evaluation forms and share with regional planning committee | Within 30 days after training
| Submit final training report to BADR and AAA(s) - Final agenda - List of attendees (including home county/tribe) - Final budget/expenditures form - Invoice for reimbursement (to GWAAR, WAND) - Summary of evaluations | Within 30 days after training OR by December 31st
| Pay bills and reimburse counties for training expenditures | Within 30 days after training |  | Fiscal Agent